## Sheet1
Royal University of Phnom Penh | [6 empty] | Faculty of Engineering
IOT ECG Monitering
|  | To be completed by: |  | Deadline: |  | Highlight Activities
|  | Electronic Solution Cambodia |  | 2023-01-04 |  | This Year [2022-2023]
Action | Responsible | Start Date | End Date | Budget | Status | Progress | Note
Week #1: Researching
ESP 32 WROOM Module |  | 20/02/2023 | 22/02/2023 | None | Started
ECG Monitioring |  | 22/02/2023 | 24/02/2023
Database |  | 24/02/2023 | 27/02/2023
Discussing | [6 empty] | We must meet up
Week #2: Hardware
ESP 32 WROOM Module |  | 2023-01-03 | 2023-02-03 | 6.5$ | Not Started
ECG Monitioring |  |  |  | 8$
PBC |  | 2023-02-03 | 2023-05-03
3d print |  | 2023-05-03 | 2023-07-03 |  |  |  | We must meet up
Week #3:
|  |  |  | None | Not Started
We must meet up
Week #4: Software
|  |  |  | None | Not Started
None
None
|  |  |  | None |  |  | We must meet up
Week #5: Software Testing
|  |  |  | None | Not Started
None
None
|  |  |  | None |  |  | We must meet up
Week #6: Software Design
|  |  |  | None | Not Started
None
None
|  |  |  | None |  |  | We must meet up